## TA00
Use Case | Goal | Paths | Code Complete | Test Passed
UC00a. Initialize Adventurer | Launch the main application for playing a specific Adventure, and the infrastructure to support it. In particular, this use case initializes the Town, Arena, and Adventure-specific Registries. | N01. Mainframe displayed as UX00 Home page: logo image, button panel, Menubar, and all registries open | 2014-08-23
| The player can also display the About box or general Help from the menu. | N02. Display Help window from menu or F1 key | 2014-08-03 | 2014-08-03
| The player can also display the About box or general Help from the menu. | N03. Display About dialog with accreditations | 2014-08-03 | 2014-08-03
UC00b. Quit Adventurer | Terminate the Adventurer program. | N01. Quit program with Adventure not open. | 2014-08-24 | 2014-08-24
|  | N02. From menu: Quit program with Adventure open. Save Hero at current location, close registries, and terminate program. | 2014-08-24 | 2014-08-24
N03. From Window close event: Quit program. Save Hero at current location, close registries, and terminate program.
N04. Restart program from last save point, with Hero in proper Building.

## TA00-Spring 2013 results
A00 Initialize Adventure: GUI Test Summary
Name | Date Passed | Test Summary | Expected Result | Test Date | Actual Results | Wireframe
Normal
N01 |  | Launch program | Splash screen displays for at least 5 seconds, then closes automatically, revealing UX00 portal view. This shows the town and arena of the current Adventure and the hero registry and dormitory. | 2013-03-06 | 3/6/13 MLM: Opens, but shows only the light blue screen with QuasQueton, Town: BilJur'Baz, and Portal to Your Adventure. This does not change until I click on it (on a MacBook, OS X). 4/8 MLM: Al said I should see a spash screen before this picture, and that isn't visible to me.
|  |  | Re-opens the last Adventure opened and its associated registries. If no Adventure was opened previously, then the default Adventure is opened. |  | I can't check that it shows anything but the default Adventure at this time.
N02 |  | Launch program with -nosplash option to view portal (From Eclipse, use the arguments tab in the Run Configuration view to enter “-nosplash” as the argument.) | Splash screen is not displayed; view goes directly to UX00 portal opening view. |  | 4/8: The splash screen is never displayed, per Al.
N03 |  | Verify portal view | Adventurer opening view matches UX00. The town, arena, and all buildings have expected names for Adventure displayed. | 2013-03-06 | 3/6/13 MLM: UX00 lists corrections to the picture that have not been made: #3, 4. Notes from UX00: #1 – There isn't an Exit link, it's buried in a menu. #2 – Help link not testable yet. Hovering over buildings does nothing yet. #3 – on a Mac, it's a single-click. Only the Inn has an action. It displays dialog box with OK button. I did not 'get' that I should click the OK. I sat and waited for the Inn to open. (I recommend changing the message to something like, 'Click OK to open the x.”) When I click OK, the left half of the screen changes to a split gray screen. I don't understand what should happen if the building is in the portal, but nothing happens on the right side of the screen. #5 and #6 can't test yet. 4/18 MLM: The text (in the pane that opens when I open the Inn) breaks in the middle of a word without a hyphen. Smoky shouldn't have an 'e' in it - that's Smokey the Bear (or cop), not a smoky room. :-) The Command line field and the bottom of the game window are below the bottom of my screen and I can't find a way to change that (MacBook, OS X). I don't get to see the splash screen, either. Al said the Arena should be labeled Stadium. The command line doesn't work, not even for exit. Al said there are little decoration thingies around the building names in the picture that might not belong in the picture. When I have the Inn open, and then click to open it again, it opens a second text editor pane next to the first! Al said the text should be at the bottom of the pane, not at the top.
N04 |  | Launch program with different (non-default) Adventure. | Different Adventure has different set of building names. Adventurer opening view matches UX00 but with non-default Adventure names, appropriate for new Adventure. Hero list is the same.
N05 |  | Use an Adventure with only Inn and Arena. | Other portal images have no name.
N06 |  | Use an Adventure with Inn, Arena, and one Guild. | Verify proper naming and that other portal images have no name.
N07 |  | Make no Adventure available to player. | Verify that default Adventure comes up.
N08 |  | Delete Hero in Hero registry. | Ensure that Hero is removed from the view.
N09 |  | Add Hero to Hero registry. | Ensure that the new Hero appears in the view.
N10 |  | Click the Help link | Help displays the proper help text in its own window for the portal view (a general description of Adventurer, how to get started, and how to get help during Adventure play). It also explains floating help.
It should replace the portal side when the text comes up.
N11 |  | Hover over each building, including dormitory and registrar. | On hover, each item displays its proper description and purpose.
N12 |  | Click the About button, then click the OK button. | About shows proper text (game credits, version number and date, and copyright). It closes with OK button. Verify that data shown in the About window is correct. | 2013-03-06 | 3/6/13: There is no About button, but clicking the menu options Help –> About displays a text box with game credits, copyright, version/build numbers, and an OK button. Should both version 1 and 2 appear with dates? OK button closes it properly.
civlauncher has a menu bar. The About screen for it only shows a version number, nothing else.
N13 |  | Click Adventure -> Exit, then click Yes. | Exit displays confirmation prompt. 'Yes' response terminates program. Verify that it doesn't merely close window and keep running. Verify that proper saving occurred. {How do I verify that this saving occurred?} Reopen and see if saved data now appears, or is in pre-saved state. | 2013-03-06 | 3/6/13: There is no confirmation prompt for Yes, at least on a Mac. When I click Exit, it closes instantly. I'm not sure if it closes completely or not, so I put a screen cap of most of my activity monitor (after doing an Exit from Adventurer) beginning at about row 45 below. 4/8: Clicking Adventure - Exit causes nothing visible to happen. The only way to close is to use the red close-window button (in OS X) or to quit civLauncher.
N14 |  | Click Adventure -> Exit, then do nothing. | Exit displays confirmation prompt. No response returns to last state of the view. | 2013-03-06 | 3/6/13: Fail, see note in row 15.
N15 |  | Click Adventure -> Exit, then click Yes. | Exit saves all open heroes. (Other saves are tested by those particular use cases.) {How do I verify that these heroes have been saved?} Create a new Hero, close and save, then reopen to see if new Hero appears.
N16 |  | Exit by window icon. | Confirmation prompt is displayed and data is saved correctly. {How do I verify that the saved state is correct?} | ?? | 3/6/13: civ.Launcher → Exit also closes the application instantly, without a confirmation prompt. I think that on a Mac, this is like exiting with the window icon.
N17 |  | Double-click on registrar. | Use case 1 is triggered. The New Hero Input panel will replace the left side of the screen, and a picture of the Registrar will replace the right side (portal view). |  |  | UX002
N18 |  | Double-click on dormitory. | Use case 3 is triggered. The list of Heroes will replace the left (Dormitory/Registrar) view, allowing one to four Heroes to join a team. The Hero selection screen is a double list view, allowing the user to move selected Heroes into the Team list, and then move them into turn order. See UX00b. Hero Selection Panel. |  |  | UX005
N19 |  | Double-click on any named building. | If a team is active (at least one Hero is in the team), use case 4 is triggered. If the Building is in the portal, the portal view will be replaced with a picture of that building, and the left side will be replaced with text about interactions with the building.
N20 | 2013-03-06 | Click or double-click on anything except a named building. | Verify that the user is NOT taken into the portal, and does not get an error message. Nothing should happen. |  | 3/6/13: Nothing happens when I click elsewhere.
N21 |  | Hover over anything except a building | Nothing new should be displayed
N22 |  | Hover over town or arena | General description of the town or arena, but you cannot enter these from portal view.
N23
ERROR
E01 |  | Remove two needed registries. | Error message is displayed before the registries are used.
E02 |  | How to test corrupted registries? | Error message is displayed before the registries are used. |  | Move this test to integration testing; not a GUI test.
E03 | 2013-03-06 | Click on each menu command | Until they are implemented, the msg is displayed 'The x command is not yet implemented. | 2013-03-06
E04 |  | Launch a second Adventurer while a first one is still running. | “Adventure already running” error message is displayed.
E05 |  | Try to open program without even the default Adventure available to player. | Registry not found error; default Adventure should always be available.
E06 |  | Try to Enter a Building in the portal without an active Hero. | Portal displays the no-Hero or “no active team” error message.
E07 |  | Open an Adventurer that QM has not “deployed” | “Invalid Adventure” or Adventure not found error message. |  | This applies to entering Adventure names from the command line, and is not possible from the GUI launch icon.
E08 |  | Double-click on any named building when a team is not active (there are no Heroes on the team). | Error message is displayed that a Hero must be awake first.
E09 | 2013-03-06 | Double-click on a named building when the building is not implemented. | Error message 'Not Implemented Yet' is displayed. | 2013-03-06 | The message, “X is not working yet.” is displayed for every building except the Inn. This is a slightly different message, but I think users will generally prefer 'working' for 'implemented.' :-)
E10
BOUNDARY
B01
B02
SPECIAL
S01
S02
S03
| 3 | 31 |  | 8
| # Passed | # Tests |  | # Tested